## Estimation Summary
Estimation Summary of FieldNET app
Service Request #
Service Request Description |  | Estimate Details of FieldNET App.
|  | Lower Limit | Upper Limit (10% buffer) | As a practice we would like to have Upper Limit & Lower Limit for a Project
|  | 366 | 402.6
Development Phases | 100% | Person Hours Lower | Person Hours Upper
Requirement Analysis & Estimation | 5% | 18.3 | 20.13 | Discuss Requirements with Client to understand the business need, get queries clarified
Design | 10% | 36.6 | 40.26 | a) Requirment doc/ Approach doc / Arch b) Estimation
Build Phase
Coding & Unit Testing | 45% | 366 | 402.6 | 1) Coding and Unit Testing 2) Code Reviews & Rework
Test Scenario Preparation | 15% | 54.9 | 60.39 | Test Scenarios , Review and Rework
Review/Rework | 5% | 18.3 | 18.3 | Requirement Traceability Matrix
Integration Testing
System testing | 15% | 54.9 | 60.39 | System Testing, Capturing Test results which includes dependency testing
Production Support
Client Testing & Support | 5% | 18.3 | 20.13
Implementation Effort |  | 567.3 | 622.2
Project Management |  | 56.73 | 62.22
Total Effort |  | 624.03 | 684.42
Note: a)Training Video's would be planned and estimated on a need base, which would be prior approved by Customer team b) Any bugs identified by Customer during UAT, on sign off by AppShark in QA environment would be AppShark's Responsibility and will not be billed to Customer c) Once Customer gives its sign off the code and the application is deployed on necessary servers and systems, a week after deployment would be treated as Production support. d) Application deployment effort is not included at the individual SR level. All the completed requirements will be delivered at once on the planned release date and the hours will be planned on a need base or on the planned release date. e) Android phones that would used for testing are Samsung 4.x and HTC4.x -- Other phones and versions wouldn't be considered for UAT.

## Coding Effort
Development Effort and unit Testing
| Total Effort | 366
Coding and Unit Testing of FieldNET app Functional Points
Task ID | Description | Hours
Android Effort
| Display of listview which consists of Drip control name, status icon and current status. | 6
| Storing details into local database of list view | 5
Dashboard
| Display of Dashboard Overlay and its class implementation | 3
| Display that details on the dashboard based on the service response | 4
| Action Bar -- Displaying Equipment button , Equipment name and Edit/ Save button | 2
| Communication Bar with service connectivity and update UI | 5
| Current Status UI | 3
| Service call to update Plan Progress Bar and its background service to update the Progress. Note: Default control would be used for Progress BAR. | 8
| Display the start time | 2
Pause, Stop and Start Service calls We assume this is for the future phase based on the revised document
| Primary sensor data display in the form of Gauge | 4
| Secondary Sensor Data service calling and display | 9
| Plan Steps Display | 3
| Inclusion of status of current plan | 2
| History Display | 3
| History Detail Screen. Equipment button click event is considered with storing the previous state. | 4
| Storing details into local database of dashboard | 12
Edit mode display NOTE: BASED ON THE CHANGE OF DISPLAYING MEU OPTION, WE HAVE REMOVED THE ESTIMATE 2 HRS FOR EDIT MODE DISPLAY
| Providing Edit MENU with animation | 4
| Change Plan Component, need to implement a custom component Note: There could be some limitation to display the arrow pointer as shown in the PDF file however we will try to develop a custom component based on the overlay of two different components for this view. Estimate has been increased as the control has to be displayed in three different section with actions. We also recommend to have previous button, as the space would be a constraint, recommend to have arrow icons. | 18
| Validation for the selected Plan computation and message display | 6
| Manage Schedule | 6
| Edit Mode of Manage Schedule | 3
| Update to Service with the updated info of manage schedule | 3
| Filter Flush with update to service | 3
| Enable Temperature Protection with update to service | 3
| Map View Note: Estimate is provided based on the PDF Visual and our POC. We are still skeptical about this as in our call, we have been told that this is a crucial and its take more time for implementation, but however based on our POC, we are able to display zones and images(which are in GREY, BLUE and RED status of zones) | 12
| Help screen implementation | 4
| Messages and pop-up alerts | 6
| Applying Lint Tool to do the static code analyzer | 8
| Unit Testing of App | 31
iOS Effort
| Display of listview which consists of Drip control name, status icon and current status. | 6
| Storing details into local database of list view | 5
Dashboard
| Display of Dashboard Overlay and its class implementation | 3
| Display that details on the dashboard based on the service response | 4
| Action Bar -- Displaying Equipment button , Equipment name and Edit/ Save button | 2
| Communication Bar with service connectivity and update UI | 5
| Current Status UI | 3
| Service call to update Plan Progress Bar and its background service to update the Progress. Note: Default control would be used for Progress BAR. | 8
| Display the start time | 2
Pause, Stop and Start Service calls
| Primary sensor data display in the form of Gauge | 4
| Secondary Sensor Data service calling and display | 9
| Plan Steps Display | 3
| Inclusion of status of current plan | 2
| History Display | 3
| History Detail Screen. Equipment button click event is considered with storing the previous state. | 4
| Storing details into local database of dashboard | 12
Edit mode display NOTE: BASED ON THE CHANGE OF DISPLAYING MEU OPTION, WE HAVE REMOVED THE ESTIMATE 2 HRS FOR EDIT MODE DISPLAY
| Providing Edit MENU with animation. Note: This is an integration of third party tool | 6
| Change Plan Component, need to implement a custom component Note: There could be some limitation to display the arrow pointer as shown in the PDF file however we will try to develop a custom component based on the overlay of two different components for this view. Estimate has been increased as the control has to be displayed in three different section with actions. We also recommend to have previous button, as the space would be a constraint, recommend to have arrow icons. | 18
| Validation for the selected Plan computation and message display | 6
| Manage Schedule | 6
| Edit Mode of Manage Schedule | 3
| Update to Service with the updated info of manage schedule | 3
| Filter Flush with update to service | 3
| Enable Temperature Protection with update to service | 3
| Map View Note: Estimate is provided based on the PDF Visual and our POC. We are still skeptical about this as in our call, we have been told that this is a crucial and its take more time for implementation, but however based on our POC, we are able to display zones and images(which are in GREY, BLUE and RED status of zones) | 12
| Help screen implementation | 4
| Messages and pop-up alerts | 6
| Applying interface for checking memory leaks and warnings. | 8
| Unit Testing of App | 31